## Sheet1
Task ID	Task	Assigned To	Planned Start	Planned End	Predecessor
1	Meet customer	Team	08/11/19	08/12/19
1.1	Define Requirements	Team	08/11/19	08/12/19
2	Design Database	Senay, Adrian, Seyed	08/15/19	11/02/19
2.1	Create weather data file	Senay	08/15/19	09/10/19
2.2	Generate random electricity usage	Senay	09/10/19	10/03/19
2.3	Generate random water usage	Senay	10/03/19	10/20/19

3	Design Front-End	Gentry, Chris, Preston	09/01/19	11/08/19
3.1	Create basic stats page template	Gentry	09/01/19	10/26/19
3.2	Create map documents	Gentry	10/26/19	11/02/19
3.3	Create Template for front-end pages	Chris	09/01/19	10/03/19
3.4	Create dashboard/switchboard functionality	Chris, Preston	10/03/19	11/04/19
3.5	Style app pages	Chris, Preston	11/04/19	11/12/19

4	Showcase app	Team	11/15/19	11/15/19